ONLINE CLIMATE RESILIENT HEALTH FOR OUR COMMUNITIES, MEDICAL CAMP SECOND EDITION  
MEETING HELD ON 23 OCTOBER 2024.

AGENDAS;

1. Progress update
2. Ground visit report
3. Programme overview
4. New partnerships
5. Volunteers coordination
6. Fundraising plan
7. AOBs

The meeting started at 2007hrs with an opening prayer from George. The minutes were read by Mulekani and confirmed by Shirleen. Each member gave a brief introduction of themselves.

MIN 1/23; PROGRESS UPDATE.

. DATA

> System set up is complete and ready for the testing phase which is to be done and confirmed by George effectively for monitoring and evaluation.

> The health management system will be the last item to be completed.

. DAYSTAR

> Confirmed o onboarding 10 volunteers per day for the 5 days camp.

> Still waiting on transport facilitation confirmation from their dean.

.MKU

> The MKUHSA president is still doing follow ups with the school.

> They proposed a 3 day transport facilitation of 14 students each.

. GREEN DADA

> Confirmed their onboarding and roles to be played as per the previous meeting.

> They will help in coordination of the tree planting session as well as taking lead of the band during inauguration.

. MEDIA

> The live video coverage is almost completed by Rawlings and will be aired by Friday.

. IPPNW

> They are handling logistical support for their volunteers.

> All members already filled the application form.

MIN 2/23; GROUND VISIT REPORT.

> On 17th Bill, Charity, Newton, George and Petronilla visited the church and later on proceeded to GK Prison Kitengela where planting of the saplings will take place.

> Head of GK confirmed and offered farmland but reduced the number of saplings to 150 due to water challenges.

> A video coverage was taken which will be shared in the group .

>Procession from the venue to the tree planting grounds will include 50 participants that is 2 representatives from each organization.

MIN 3/23; PROGRAMME OVERVIEW

> The programme was shared for confirmation by the team and only few edits are to be made.

> The head representative of each organization are to reach out to Charity in line with that.

MIN 4/ 23; NEW PARTNERSHIP.

> New partners were identified and reached out to for assistance in bridging the financial gap yet still awaiting feedback from them. They include; KMA Circle, Britam, Jubilee, UNICAF, CIC GROUP.

MIN 5/23; VOLUNTEERS COORDINATION.

> Confirmed a total of 143 registered volunteers already. Both health and climate campaign will have a leading team.

> Dr. Alerton and Dr. Freedah under the clinical department will need a database for duty roaster which they will liase with the nurses for roles allocation.

> The pharmaceutical department to provide a list of medical supplies for allocation.

> Evaluation of the camps success for documentation to be conducted.

> All communication will be done on the whatsapp group.

MIN 6/ 23: FUNDRAISING PLAN.

> The team is still having a high budget deficit and calling upon ideas on bridging the gap. Laergest budget is on meals facilitation as well as ambulance.

> Proposal was made on organizations to chip in apart from the student organizations.

MIN 7/23: AOBs

> A brief meeting should be conducted on the WhatsApp group by Friday.

> Charity is to share a spreadsheet for the camp session.

> Dr. Samaan is to confirm on the pharmaceutical products to be brou ght in to proceed by Dr. Alerton.

> Elder Nancy is to help coordinate the welfare and counselling outreach.

The meeting ended with a word of prayer from Elder Nancy at 2123hrs. The next meeting will be held on 30th October at 2000hrs.